## README
Risk Treatment Plan
Credit Decisioning Assistant (CDA) — Artefact A-11 ¦ Governance design artefact, worked example
Field | Detail
Purpose | For every risk on the register: the treatment chosen, why that treatment over the alternatives, the owner, the completion evidence, and the verification that it worked.
Why Treatment Rationale Is Recorded | A treatment with no recorded rationale cannot be reviewed. When circumstances change, the question is whether the reasoning still holds — which requires knowing what it was.
Four Treatment Types | Avoid, Reduce, Transfer, Accept. Zero-appetite risks may not be treated by Accept. A treatment marked Accept must name an individual accepting role, not a committee.

## SUMMARY-DASHBOARD
Risk Treatment Plan - Executive Summary Dashboard
System: Credit Decisioning Assistant (CDA — Artefact A-11) ¦ Review Date: 14-Sep-2026 ¦ Governing Body: AI Governance Committee
Treatment Type | Total Risks | Completed / Verified | Active in Production | Accepted with Condition | Est. Total Budget / Effort | Operational Highlights & Key Controls
Reduce (Mitigate) | 18 | 9 | 9 | 0 | Internal: 220 engineer-days; Tooling/Audits: GBP 80,000 | Enforces structural controls: GDR-01/02/03/04, ENF-01, S3 Object Lock, 2-sided override band, and Brier calibration.
Transfer + Reduce | 1 | 0 | 1 | 0 | External Legal Review: GBP 12,000 | Contractual training exclusion and data residency covenants in enterprise AWS Bedrock agreement (R-10).
Accept with Condition | 1 | 0 | 0 | 1 | Quarterly review: 8 days/year | R-12: GDR-06 entailment unavailable in ap-southeast-1; accepted with mandatory underwriter citation check compensating control.
Avoid | 0 | 0 | 0 | 0 | N/A | Zero use-case avoidances required post-screening; all adopted risks treatable within enterprise risk appetite.
TOTAL | 20 | 9 | 10 | 1 | Internal: 220 engineer-days; Audits: GBP 92,000 | 20 risks treated across scoring, narration, orchestration, data, and vendor layers. 100% verification coverage established.

## VERSION-CONTROL
Version and Approval History
Version | Date | Author | Reviewer | Approver | Status | Change Summary
v1.0 | 2026-02-10 | AI Governance Lead | Risk | AI Governance Committee | Superseded | Initial plan
v1.1 | 2026-03-06 | AI Governance Lead | Model Risk | AI Governance Committee | Superseded | R-11 treatment and closure evidence
v1.2 | 2026-09-10 | AI Governance Lead | — | Pending | Draft | Alternatives-considered tab added; aligned to A-numbering and D1–D7

## TREATMENTS
Risk Treatment Plan - Detailed Operational Actions and Verification
Separation of control installation from empirical verification. Residual risk reflects verified operational effectiveness.
Risk | Treatment Type | Treatment Description | Interim Controls | Primary Owner | Supporting Teams | Resources / Budget Estimate | Success Criteria (Threshold) | Target / Completed Date | Target Residual Score | Target Priority | Next Review Date | Verification Method | Status | Evidencing Artefact | Treatment & Rating Rationale
R-01 | Reduce | Grounding verification blocks unsupported responses; mandatory citation to a specific passage; officer check 2 | 100% manual underwriter inspection of all drafted adverse-action citations prior to applicant issuance | AI Governance Lead | MLOps, Model Risk, Underwriting Ops | Internal: 20 engineer-days; Model Risk validation: 5 days | Grounding score >= 0.75 floor; 100% passage citation resolution; ungrounded outputs blocked, not flagged | 2026-03-09 | 8 (2×4) | MEDIUM | 2026-11-15 | Effectiveness test against a labelled question set | Complete | A-39 GDR-04 | Inherent Score 20 (L=4, I=5) reduced to Residual Score 8 (L=2, I=4). Target Priority achieved at MEDIUM. Zero appetite for ungrounded citations. Automated block-on-fail prevents hallucinated rationale from reaching underwriter.
R-02 | Reduce | Six-entity redaction incl. national identifier, applied before output and before record is written | Tokenized mock customer test data; ingress payload inspection by security analyst | DPO | Data Protection, Security Architecture, Data Engineering | Internal: 15 engineer-days; DLP tooling: GBP 12,000 | 0 unredacted PII instances in narration output or audit logs; 100% recall on 6 entity types (NRIC, name, address, phone, email, account no.) | 2026-03-09 | 8 (2×4) | MEDIUM | 2026-11-15 | Sample records inspected for pre-redaction content | Complete | A-39 GDR-03, LOG-02 | Inherent Score 15 (L=3, I=5) reduced to Residual Score 8 (L=2, I=4). Target Priority: MEDIUM. Zero appetite. Statutory GDPR/PDPA compliance requires sanitization before logging to persistent WORM storage.
R-03 | Reduce | Prompt-attack filtering on input; adversarial suite re-run quarterly; XML input delimiter separation | Pre-deployment black-box penetration testing and strict free-text character length caps (250 chars) | Security Architecture | SecOps, Red Team, MLOps | Adversarial red-team audit: GBP 25,000; Internal dev: 12 engineer-days | 100% block rate across 150 benchmark injection test vectors; zero delimiter escape in red-team suite | 2026-03-08 | 6 (2×3) | LOW | 2026-11-15 | 100% block rate on the adversarial set | Complete | A-39 GDR-01 | Inherent Score 16 (L=4, I=4) reduced to Residual Score 6 (L=2, I=3). Target Priority: LOW. Managed via AWS Bedrock Guardrails (GDR-01) input filtering and quarterly penetration testing.
R-04 | Reduce | Denied-topic control with explicit definition and worked examples in safety system prompt | Compliance manual spot-check of all pilot loan narration transcripts | Compliance | Legal, Product, AI-CoE | Compliance review: 5 days; Prompt engineering: 4 days | 0 instances of investment/advisory phrases; 100% block rate across 40 adversarial advisory probe prompts | 2026-03-08 | 4 (1×4) | LOW | 2026-11-15 | 40 prompts soliciting investment guidance, all blocked | Complete | A-39 GDR-02 | Inherent Score 15 (L=3, I=5) reduced to Residual Score 4 (L=1, I=4). Target Priority: LOW. Zero appetite for unlicensed financial advice under MAS FAA / UK FSMA. Controlled via GDR-02 denied-topic rules.
R-05 | Reduce | Permission-layer denial (ENF-01); governed exception path (ENF-02) with real-time SIEM alarm | VPC security group restrictions and API gateway token authentication | Security Architecture | SecOps, Cloud Infrastructure, Platform Engineering | Cloud engineering: 10 engineer-days; SIEM alert rules: 3 days | 100% un-guardrailed Bedrock invocations return HTTP 403 Access Denied; SIEM P1 alert triggers within 30 seconds | 2026-03-14 | 5 (1×5) | MEDIUM | 2026-10-15 | Denial demonstrated, not asserted. Alarm confirmed firing | Complete — risk stays open | A-39 ENF-01, ENF-02 | Inherent Score 10 (L=2, I=5) reduced to Residual Score 5 (L=1, I=5). Target Priority: MEDIUM. Zero appetite. Controls cannot reduce impact 5 (ungoverned model use remains catastrophic); likelihood reduced to 1 via IAM locks.
R-06 | Reduce | Architecture with no standing cost; zero-spend alarm; teardown covering every billable component | AWS daily budget ceiling alerts set at $50/day during pilot | AI Governance Lead | FinOps, Cloud Architecture | FinOps pipeline automation: 6 engineer-days | $0 idle compute spend during non-operating hours; zero-spend CloudWatch billing alert functional | 2026-03-25 | 4 (2×2) | LOW | 2026-12-01 | Cost verification post-deployment | Complete | A-41 §4 | Inherent Score 8 (L=4, I=2) reduced to Residual Score 4 (L=2, I=2). Target Priority: LOW. Serverless on-demand endpoints eliminate standing cluster infrastructure costs. Closed at Gate 5.
R-07 | Reduce | Version change as a mandatory review trigger; no production traffic on an untested version | Version pinning in AWS Bedrock invocation ARN; daily automated endpoint version check | AI Governance Lead | Model Risk, Procurement, MLOps | Model migration test harness: 15 engineer-days; Re-validation: 8 days | Zero production traffic routed to un-attested foundation model snapshot; deprecation logged >= 60 days before EOL | Ongoing | 4 (1×4 post-cutover) | MEDIUM | 2026-10-15 | Trigger rules published; deprecation watch reviewed monthly | Active | A-40 | Inherent Score 12 (L=3, I=4); Current Residual 8 (2×4); Target Residual Score 4 (1×4) post-cutover. Target Priority: MEDIUM. Zero appetite for untested version cutover. Active deprecation notice logged in A-40; re-validation scheduled for Q4 cutover.
R-08 | Reduce | Two-sided override band (15%–40%); competency attestation; below-band escalates as control failure | Weekly manual underwriting audit sample of 25% of auto-approved / auto-narrated loans; circuit breaker: halt narration if override < 10% for 2 months | Loan Operations | Credit Underwriting, HR Training, Model Risk | Underwriter training & curriculum: GBP 18,000; Dashboard dev: 8 engineer-days | Monthly underwriter override rate sustained between 15% and 40%; median review duration >= 3.5 minutes floor | Ongoing | 8 (2×4 post-training) | MEDIUM | 2026-10-01 | Monthly measurement against the band | Active | A-36 §6, A-38 | Inherent Score 15 (L=3, I=5); Current Residual 12 (3×4); Target Residual Score 8 (2×4) upon underwriter competency certification. Target Priority: MEDIUM. Behavioral oversight decay managed by continuous telemetry; below 15% triggers automation bias investigation.
R-09 | Reduce | Corpus change as a mandatory trigger; monthly integrity check against the recorded version | SharePoint document freeze; manual change sign-off from Head of Credit Policy | AI Governance Lead | Credit Policy, MLOps, Data Engineering | Integrity check automation: 6 engineer-days | 0 unlogged corpus modifications; 100% cryptographic SHA-256 hash match between live index and baseline A-14 | Ongoing | 6 (2×3) | LOW | 2026-11-01 | Monthly check; no unlogged change to date | Active | A-14 §5 | Inherent Score 12 (L=3, I=4) reduced to Residual Score 6 (L=2, I=3). Target Priority: LOW. S3 Object Lock and monthly automated Lambda sweeps prevent silent policy manual revisions from invalidating vector retrieval.
R-10 | Transfer + Reduce | Contractual training exclusion and residency; annual due diligence; deprecation as a trigger | Legal assessment of AWS Customer Agreement and Data Processing Addendum (DPA) | Procurement | Legal Counsel, Vendor Risk Management, CISO | External legal review: GBP 12,000; Vendor audit: 5 days | Binding enterprise addendum executed guaranteeing zero model training on customer data & ap-southeast-1 residency | Ongoing | 6 (2×3) | LOW | 2026-12-15 | Due diligence record; verification dates in the model registry | Active | A-17, A-18 | Inherent Score 12 (L=3, I=4) reduced to Residual Score 6 (L=2, I=3). Target Priority: LOW. Third-party vendor dependency risk transferred via enterprise BAA and managed via contractual termination/deprecation covenants.
R-11 | Reduce | Metadata field removed; address added to redaction; prompt constrained; checklist prompt Q2.4 added | Gate 2 hard block; production deployment halted until re-test passed threshold | AI Governance Lead | Model Risk Analytics, Data Engineering, Legal | Remediation engineering: 25 engineer-days; Counterfactual bias re-test: 10 days | Disparate Impact Ratio >= 0.80 across all planning segments; postal metadata 100% stripped from retrieval chunks | 2026-03-02 | 5 (1×5) | MEDIUM | 2026-10-01 | Counterfactual re-test at 0.89 against a 0.80 threshold | Complete | A-15 BFT-008 | Inherent Score 15 (L=3, I=5) reduced to Residual Score 5 (L=1, I=5). Target Priority: MEDIUM. Zero appetite. Gate 2 blocked at DIR 0.67; root cause resolved by deleting postal metadata. DIR restored to 0.89. Closed at Gate 2.
R-12 | Accept | No treatment available — capability unavailable in required jurisdiction. Compensating control only | Mandatory passage-level citation verification checklist enforced for all reviewing underwriters | AI Governance Lead (named accepting role) | AI Governance Committee, Model Risk | Quarterly cloud feature availability assessment: 2 days/quarter | 100% adverse-action rationales cite verbatim passages; senior underwriter review on all contested reasoning | 2026-03-11 | 12 (3×4) | HIGH | 2026-10-15 | None. Accepted with quarterly availability review | Accepted | A-24 CONSTRAINTS | Inherent Score 12 (L=3, I=4) carries Residual Score 12 (L=3, I=4). Target Priority remains HIGH. GDR-06 logical entailment unavailable in-region. Formally accepted with condition by named AI Governance Lead, backed by underwriter Check 2.
R-13 | Reduce | Independent re-review by a different officer within 10 working days; reversal rate monitored (A-37) | Standard customer complaints logging mailbox with manual escalation to credit committee | Compliance | Lending Operations, Customer Service, Legal | Recourse workflow system build: 18 engineer-days; Operational procedures: 6 days | Independent re-review SLA <= 10 working days; underwriter reassignment enforced (cannot re-assign to original reviewer) | 2026-03-20 | 4 (1×4) | LOW | 2026-11-15 | Procedure approved as a precondition of go-live | Complete | A-37 | Inherent Score 12 (L=3, I=4) reduced to Residual Score 4 (L=1, I=4). Target Priority: LOW. Zero appetite. Statutory contestability gap resolved by establishing Customer Recourse Procedure (A-37) prior to pilot go-live.
R-14 | Reduce | Annual retrieval verification; retrieval tested as part of each recourse case; WORM storage | Daily manual database backup dumps of credit decision payloads | AI Governance Lead | Cloud Operations, Internal Audit, Compliance | Immutable log pipeline dev: 10 engineer-days; Annual audit retrieval test: 4 days | 100% of audit records, model cards, and prompt telemetry retrievable within 24 hours over 7-year retention window | Ongoing | 6 (2×3) | LOW | 2026-12-01 | Annual test scheduled | Active | A-41 §6 | Inherent Score 8 (L=2, I=4) reduced to Residual Score 6 (L=2, I=3). Target Priority: LOW. Centralized S3 log archive with Object Lock compliance mode guarantees immutable evidence for regulatory inspection.
R-15 | Reduce | ROC-AUC 0.78 and F1 0.65 minimum gates; feature adequacy review before Gate 4 re-presentation | Manual credit underwriter co-validation of 100% of borderline automated approvals | Head of Model Risk | Data Science, Credit Risk Analytics | Feature engineering & benchmark re-training: 22 engineer-days | Production scoring model ROC-AUC >= 0.78 and F1 >= 0.65 (achieved 0.847 in benchmark testing) | Ongoing | 8 (2×4) | MEDIUM | 2026-11-01 | Model Risk independent validation against matured test partition | Active | A-12, A-39 VAL-01 | Inherent Score 15 (L=3, I=5) reduced to Residual Score 8 (L=2, I=4). Target Priority: MEDIUM. Zero appetite for underperforming models. Independent validation verified AUC 0.847; monitored on live pilot batches.
R-16 | Reduce | Generalization gap against 5-point AUC tolerance on holdout partition held by Model Risk | 5-fold stratified cross-validation during feature development iterations | Head of Model Risk | Data Science, Model Risk | Holdout partition governance: 8 engineer-days | Train-to-test generalization gap <= 5.0 AUC points on unseen holdout dataset (achieved 2.1 points) | 2026-05-15 | 8 (2×4) | MEDIUM | 2026-11-01 | Holdout test partition evaluation released once by Model Risk | Complete | A-12 §4 | Inherent Score 12 (L=3, I=4) reduced to Residual Score 8 (L=2, I=4). Target Priority: MEDIUM. Closed at Gate 4 after single-blind holdout evaluation confirmed generalization gap of 2.1 points, comfortably below 5.0 tolerance.
R-17 | Reduce | Brier monitored against 0.18 tolerance on live outcomes; HITL marginal band tied to probability scale | Quarterly probability calibration curve review and manual underwriter queue threshold checks | Head of Model Risk | Data Science, MLOps, Underwriting Operations | Isotonic calibration pipeline: 12 engineer-days; Calibration telemetry: 4 days | Brier calibration score <= 0.18 on live matured cohorts (achieved 0.13); marginal band +/-0.05 around cutoff | Ongoing | 8 (2×4 post-recalib) | MEDIUM | 2026-10-01 | Monthly Brier score calculation against 30/60-day matured loan delinquency outcomes | Active | A-10 FM-03, A-36 | Inherent Score 12 (L=3, I=4); Current Residual 12 (3×4); Target Residual Score 8 (2×4) following live recalibration. Target Priority: MEDIUM. Probability scale miscalibration silently misroutes borderline loans; monitored continuously against 0.18 threshold.
R-18 | Reduce | Rolling AUC against matured outcomes; decay beyond 3 points triggers retraining assessment | Weekly Population Stability Index (PSI) tracking on credit bureau scores and income features | Head of Model Risk | MLOps, Credit Analytics, Risk Committee | SageMaker Model Monitor deployment: 14 engineer-days; Retraining pipeline: 20 days | Rolling ROC-AUC degradation <= 3.0 points from Gate 4 baseline; feature PSI <= 0.20 | Ongoing | 8 (2×4 post-retrain) | MEDIUM | 2026-10-01 | Automated weekly SageMaker drift alerts; quarterly formal Model Risk report | Active | A-10 FM-04, A-40 | Inherent Score 16 (L=4, I=4); Current Residual 12 (3×4); Target Residual Score 8 (2×4) upon model retraining pipeline execution. Target Priority: MEDIUM. Macroeconomic concept drift inevitable over time. Monitored via real-time PSI and 3-point AUC decay alarm triggers.
R-19 | Reduce | Per-identity rate limiting; anomalous query-pattern alarm; no per-record confidence exposure | WAF rate limit of 100 requests/minute per IP; manual investigation of suspicious query surges | Security Architecture | SecOps, Application Security, Core Banking Dev | WAF rate limiting & API token masking: 8 engineer-days | 0 raw probability outputs exposed on external interfaces; query rate limits enforced at API Gateway | Ongoing | 6 (2×3) | LOW | 2026-11-15 | API penetration test attempting systematic parameter probing; WAF rule verification | Active | A-10 FM-05, A-39 SEC-02 | Inherent Score 9 (L=3, I=3) reduced to Residual Score 6 (L=2, I=3). Target Priority: LOW. Black-box model extraction mitigated by suppressing confidence intervals on external notices and enforcing API rate limits.
R-20 | Reduce | Green/amber/red threshold treatment; circuit breaker on latency; optimisation may not weaken controls | Manual cloud resource scaling during peak underwriting hours (9:00 AM - 5:00 PM) | Platform Operations | Cloud Infrastructure, MLOps, Core Banking Dev | Auto-scaling & circuit breaker implementation: 12 engineer-days | Inference p95 latency < 1,500ms; circuit breaker trips to deterministic score within 4 minutes on breach | Ongoing | 6 (2×3) | LOW | 2026-11-01 | Synthetic latency injection test in staging environment; CloudWatch p95 telemetry | Active | A-10 FM-12, A-41 §4 | Inherent Score 9 (L=3, I=3) reduced to Residual Score 6 (L=2, I=3). Target Priority: LOW. RES-01 circuit breaker operationalized to fall back to deterministic scoring if LLM narration exceeds 1.5s p95.
Governance Note: R-05 shows 'Complete — risk stays open'. The treatment is finished; the risk is not closed because it can only materialise in production. Target Residual Scores reflect forward-looking risk targets upon full control maturation (e.g. R-08 dropping to 8 post-training, R-18 to 8 post-retraining). Next Review Dates establish the statutory calendar cadence for Model Risk and AI Governance Committee audits.

## ALTERNATIVES-CONSIDERED
Alternatives Considered - Architectural and Governance Decision Rationale
Recorded for treatments where the choice was not obvious. Defends against retrospective audit challenge by recording why alternatives were rejected.
Risk | Options Considered and Decision Taken | Governance / Architectural Principle Applied
R-11 | (a) Adjust the threshold to accept 0.67 — rejected, the threshold was pre-declared precisely so the decision would not turn on a post-hoc judgement. (b) Weight the model output to compensate — rejected, compensating for a proxy is not removing it and leaves the mechanism intact. (c) Remove the field at source — ADOPTED, structural removal rather than mitigation | Root cause removed rather than offset
R-12 | (a) Deploy in a jurisdiction where the control is available — rejected, breaches the residency requirement. (b) Defer the control and proceed — rejected, leaves the failure mode wholly undetected. (c) Accept with a compensating control and quarterly review — ADOPTED | Constraint named rather than engineered around
R-05 | (a) Policy requiring developers to attach the control set — rejected, a control depending on people remembering is a convention. (b) Application-layer check — rejected, bypassable by the calling application. (c) Permission-layer denial — ADOPTED | Enforcement placed where it cannot be bypassed
R-08 | (a) One-sided threshold rewarding low override — rejected, that is the decay signature itself. (b) Remove the metric as unmeasurable — rejected. (c) Two-sided band (15%–40%) — ADOPTED | Both ends of the band are failures, of different kinds
R-10 | (a) Build in-house to remove dependency — rejected, disproportionate. (b) Multi-vendor redundancy — rejected, doubles the governance surface for marginal benefit. (c) Contractual controls plus deprecation triggers — ADOPTED | Dependency accepted and managed rather than eliminated
R-13 | (a) Rely on standard customer service complaints inbox — rejected, unspecialized staff cannot evaluate algorithmic attributions. (b) Automated re-scoring with relaxed threshold — rejected, introduces secondary bias. (c) Independent human re-review by a different underwriter under Artefact A-37 — ADOPTED | Meaningful human contestability requires an independent human mind
R-15 | (a) Deep neural network architecture — rejected, lacks exact local Shapley value explainability required for adverse action. (b) Linear logistic regression — rejected, insufficient ROC-AUC discrimination power (< 0.75). (c) Regularized Gradient-Boosted Decision Trees (XGBoost) — ADOPTED | Explainability by design without sacrificing required risk discrimination
R-20 | (a) Cache previous narrations and serve stale rationale on timeout — rejected, serves inaccurate policy citations. (b) Block transaction entirely until LLM recovers — rejected, creates severe customer drop-off. (c) Fail to deterministic credit score with narration suppressed (RES-01) — ADOPTED | Graceful degradation must preserve credit decision integrity above narrative polish

## VERIFICATION
Verification Record - Empirical Evidence of Operational Effectiveness
Completion and verification are separate steps. This worksheet records empirical proof that the control works as designed.
Risk | Verification Type | Method Applied | Empirical Result | Verification Date | Verified By | Re-Verification Cadence
R-01 | Effectiveness | Labelled question set with known-ungrounded responses | Below-threshold responses blocked, not flagged | 2026-03-09 | Model Risk | Quarterly
R-02 | Effectiveness | Sample outputs containing each entity type; downstream records inspected | All entities redacted; none present in the log | 2026-03-09 | DPO | Quarterly
R-03 | Adversarial | Known injection patterns across 150 prompt attack vectors | 100% block rate | 2026-03-08 | Security Architecture | Quarterly
R-04 | Adversarial | 40 prompts soliciting investment guidance and financial advice | 100% blocked via GDR-02 filter | 2026-03-08 | Compliance | Quarterly
R-05 | Effectiveness | Call attempted without the control set attached | Access denied; no path reaches the model ungoverned | 2026-03-14 | Security Architecture | Quarterly
R-06 | Cost Verification | CloudWatch billing audit during non-operational pilot hours | Zero standing cluster charges confirmed; $0 spend | 2026-03-25 | AI Governance Lead | Monthly
R-07 | Configuration | Model ARN check against approved Model Registry baseline | Model pinned to bedrock.anthropic.claude-v2:1; unapproved version blocked | 2026-04-10 | AI Governance Lead | Monthly
R-08 | Behavioral | Statistical underwriter review duration and override rate analysis | Override rate 23.4% (within 15%-40% band); median duration 4.1 mins | 2026-05-30 | Head of Lending Ops | Monthly
R-09 | Integrity | Automated Lambda SHA-256 hash comparison between live index and baseline | 100% cryptographic hash match; zero unlogged edits | 2026-03-15 | AI Governance Lead | Monthly
R-10 | Due Diligence | Vendor security & contract compliance review against MAS TRM / GDPR | Enterprise BAA executed; zero training on data confirmed | 2026-03-22 | Procurement | Annual
R-11 | Effectiveness | Counterfactual pair re-test, identical design to failing test | 0.89 against a 0.80 threshold (remediated from 0.67) | 2026-03-02 | Model Risk | Quarterly
R-12 | Availability Review | Cloud provider feature roadmap inspection for GDR-06 logical entailment | Still unavailable in ap-southeast-1; compensating underwriter Check 2 active | 2026-03-11 | AI Governance Lead | Quarterly
R-13 | Configuration | Recourse routing workflow inspection and segregation-of-duties review | Re-review cannot be assigned to original reviewer; 10-day SLA enforced | 2026-03-24 | Compliance | Annual
R-14 | Retrieval | Mock audit record pull for 50 historical decisions across 6-month window | 100% records retrieved within 15 minutes; SHAP vectors intact | 2026-06-15 | AI Governance Lead | Annual
R-15 | Model Performance | Independent Model Risk evaluation on matured validation dataset | ROC-AUC 0.847 and F1 0.72 achieved (exceeding 0.78 / 0.65 floors) | 2026-05-20 | Head of Model Risk | Quarterly
R-16 | Effectiveness | Single-blind evaluation on holdout test partition held by Model Risk | Generalization gap held at 2.1 points AUC (below 5.0 point tolerance) | 2026-05-15 | Head of Model Risk | At retraining
R-17 | Calibration | Brier score calculation against 60-day matured loan performance data | Brier score 0.13 achieved (within <= 0.18 tolerance) | 2026-06-01 | Head of Model Risk | Monthly
R-18 | Drift Monitoring | Population Stability Index calculation across top 10 credit score drivers | Max feature PSI 0.11 (well below 0.20 drift alert threshold) | 2026-07-01 | Head of Model Risk | Weekly
R-19 | Adversarial | Automated black-box parameter perturbation attack against scoring API | WAF rate limit blocked query bursts; confidence suppression confirmed | 2026-06-10 | Security Architecture | Semi-Annual
R-20 | Resilience | Synthetic latency injection (3,000ms delay) into narration service | Circuit breaker opened within 1.2s; fell back to raw score with narration suppressed | 2026-06-25 | Platform Operations | Semi-Annual