## README
Governance Maturity Tracker
Credit Decisioning Assistant — Artefact A-43 ¦ Hybrid architecture: deterministic scoring layer + RAG narration layer
Field | Detail
Purpose | Tracks AI governance maturity across fifteen dimensions on a quarterly trajectory rather than as a point-in-time score. Distinct from A-06, which is the completed self-assessment; this artefact carries the movement between assessments and the constraints on how fast it can move.
Why separate from A-06 | A self-assessment answers where we are. A tracker answers whether we are moving, at what rate, and what is structurally preventing movement. Reporting a single score to the Board without the trajectory invites the assumption that maturity improves with effort, which is not true of dimensions requiring evidence over multiple cycles.
Scoring | 0 Absent, 1 Initial, 2 Developing, 3 Defined, 4 Managed, 5 Optimised. Scored against evidence, not intent.
Cadence | Re-scored quarterly at the Periodic Responsible Model Review. Reported to the AIGC each quarter and to the Board annually.

## VERSION-CONTROL
Version and Approval History
Version | Date | Author | Reviewer | Approver | Status | Change summary
v1.0 | 2026-09-10 | AI Governance Lead | Risk | AIGC | Draft | Established at the ninety-day mark following the first completed self-assessment

## TRACKER
Maturity By Dimension - Baseline And Trajectory
Q3-2026 is the baseline. Target is the position expected at the next annual assessment, not an aspiration.
Ref | Dimension | Q3-2026 | Target | Trajectory | Commentary
D1 | Leadership and accountability | 4 | 4 | Stable | Structure exercised, including a gate block. No movement expected or needed
D2 | Policy framework | 3 | 4 | Improving | Overlap between three acceptable-use policies resolved at v2.0. Operation over time not yet evidenced
D3 | AI inventory and discovery | 2 | 4 | Static | Embedded AI found retrospectively. Discovery is reactive — the binding constraint on this dimension
D4 | Risk management | 3 | 4 | Improving | Applied fully to one system; appetite calibrated to that system rather than a portfolio
D5 | Data governance | 3 | 4 | Improving | Metadata purpose declaration now mandatory. Control exists because minimisation failed at first design
D6 | Fairness and bias assurance | 3 | 4 | Improving | Strongest dimension in method. Testing remains partly synthetic; live-sample cycle incomplete
D7 | Model lifecycle management | 2 | 4 | Deteriorating | Three quarterly verification criteria currently overdue. Cadence defined and not being met
D8 | Control implementation and testing | 3 | 4 | Stable | Effectiveness coverage at 71%. One control constrained by regional unavailability
D9 | Human oversight | 3 | 4 | Stable | Two-sided band operating. One reviewer correctly blocked pending attestation
D10 | Transparency and recourse | 2 | 4 | Static | Route exists, untested against a real contested decision. Untested procedures score 2
D11 | Monitoring and incident response | 3 | 4 | Improving | Two quarterly cycles complete. Insufficient history for trend judgement
D12 | Independent assurance | 1 | 3 | Static | Internal Audit has not completed a pass. Binding constraint on the credibility of every other score
D13 | Vendor and third-party management | 3 | 4 | Stable | A vendor was actually rejected on a disclosure failure, which evidences the checklist is applied
D14 | Skills and literacy | 2 | 4 | Improving | Competency recorded and version-bound. Workforce-wide annual cycle incomplete
D15 | Decommissioning and retention | 2 | 3 | Static | Plan sound and entirely untested. No retrieval test has run
Summary
Dimensions tracked | 15
Mean current score | 2.6
Mean target | 3.9
Improving | 6
Static | 4
Deteriorating | 1
D7 is the only dimension deteriorating, and it is deteriorating through inaction rather than event: three model-selection verification criteria passed their due date and were not re-run. Shown as overdue rather than quietly refreshed, because the overdue state is the finding.

## CONSTRAINTS
What Caps Movement
Maturity above Defined generally requires evidence of operation over multiple cycles. Effort does not compress time.
Constraint type | Dimensions | Why it caps | Path to target
Time-bound | D2, D4, D11 | Dimensions requiring evidence of repeated operation cannot exceed Defined until multiple cycles have run | Not remediable by effort. Reaches target through elapsed cycles
Portfolio-bound | D3, D4 | Portfolio dimensions cannot exceed Defined while only one system has completed the lifecycle. A framework proven once is proven once | Reaches target at the second and third governed system
Capacity-bound | D12 | Independent assurance depends on Internal Audit capacity outside the governance function's control | Requires audit plan commitment. Escalated to Board Audit Committee
Evidence-bound | D10, D15 | Procedures that have never been exercised score 2 regardless of design quality | Reaches target on first real use, or on a live-fire exercise
Structural | D3 | Discovery depends on people reporting AI they encounter. No monitoring metric detects unregistered AI | Requires a systematic discovery sweep plus a vendor notification obligation

## ACTIONS
Remediation Actions
Every dimension at 2 or below carries a named action. A dimension with a gap and no action is an observation.
Ref | Movement | Action | Owner | Target | Rationale
D12 | 1 → 3 | Commission a third-line pass over the framework and one full system control set | Chief Audit Executive | 2027-Q1 | Highest priority — converts self-reported assurance into tested assurance
D3 | 2 → 4 | Systematic discovery sweep for embedded AI in third-party products; recurring vendor notification requirement | AI Governance Lead | 2026-Q4 | An inventory depending on someone noticing is not an inventory
D7 | 2 → 4 | Clear the three overdue verification criteria; automate the due-date alert rather than relying on the review meeting | AI Governance Lead | 2026-Q4 | Process gap, not design gap
D10 | 2 → 4 | Live-fire test of the recourse route with a constructed case before the first real contest | Head of Compliance | 2026-Q4 | An untested procedure is a hypothesis
D14 | 2 → 4 | Complete the first full annual workforce literacy cycle and report completion rate | HR with AI-CoE | 2027-Q1 | Art.4 obligation is continuous, not one-off
D15 | 2 → 3 | Run the first annual archive retrieval test against live evidence storage | AI Governance Lead | 2026-Q4 | Closes the open audit-retrievability risk